## Sheet1
Date | Contact | TaskName | Email | Phone | Notes
February | LH, DJS & Com | Decide on time & date |  |  | Lynley Hutton WSS Pres
February | LH, DJS & Com | Decide on venue
February | LH, DJS & Com | Decide on Guest Speaker options
February | DJS/LH | Invite Guest Speaker
February | LH, DJS & Com | Decide on Programme speakers
February | LH/DJS | Liaise with caterer
March | JD | Design Invite flier
March | LH/BP/Interns | Circulate Invite Flier incl social media
March | Interns | Contact Seniors, Youth, Service groups
March | RG | Collate bookings |  |  | Robert Gordon WSS
March | DJS | Liaise further with Speakers
March | BP/Interns | Find quotes & type up Prog
March | LH/DJS | Write Press Release
March | Interns | Circulate Media Releases & Social Media
March | RG | Maintain databases of attendees
April | DJS | Print programmes for table
April | DJS/LH | Prepare & Send Run Sheet
April | LH/NC | Bring Name Tags |  |  | Neil Coup
April | DJS | Bring Bruce Mason Sonnet
April | DJS | Take List
April | JD/DJS | Asssemble Take List items
April | DJS/JD/Dirs | Final communication venue re # & details
April | LH/BP/DJS | Set Up venue
April | ALL | Bard's Birthday Dinner
April | JD/DJS | Narrative Reporting
April | DJS | Thank Yous
April | RG | Payments