## Sheet1
Date | Contact | TaskName | Email | Phone | Notes
October22 | DJS | Book Tolcarne Boarding Residence
June | DJS | Contact Seles Nat UO
June | DJS | Issue rest of Contracts
June | DJS | Request all Dir & Tut Bios & Photos
June | JD | Type up programme with above
June | DJS | Confirm Travel Liaison
June | DJS/JD | Confirm Assistant Supervisor/Production Manager
June | DJS/JD | Finalise Full List
June | DJS | Reconfirm with UO
June | DJS | Prepare & Send Information Pack 1
June | DJS/JD | Prepare & send funding apps
June | JD | Prepare & maintain databases
July | BP/JD | Process & Record Returns
July | JD | Reconcile payments
July | JD/BP | Find photos
July | DJS | Confirm Alumni Liaison
July | DJS/EC | Confirm Travel Liaison Erina
July | JD | Articles to Magazines
August | JD | Prepare Social Media &PR Plan
August | DJS | Obtain Rooming Plan
August | DJS/JD | Prepare & send funding apps
August | DJS/RG | Provide lists studs & drivers
August | Vols | Prepare Bag Tags
August | DJS | Write article
August | JD/DJS | Prepare & send funding apps
August | DJS | Confirm spaces required
August | DJS/JD | Organise Mystery Tour
August | DJS/JD | Prepare Info Pack 2
August | DJS | Receive all scripts
August | JD/DJS | Send scripts
August | JD/DJS | Send out Info Pack 2
August | DJS/JD | Secure Production Team
September | JD | Design Poster/Prog Cover
September | JD | Check students' info all rec'd
September | DJS/JD | Finalise engagements
September | DJS/JD | Create Groups
September | JD | Group details lists
September | DJS | Link Dirs w Costumier & Composer
September | DJS | Organise Sat Morn MT
September | DJS | Finalise Schedule
September | DJS/JD | Book bus
September | DJS/JD | Design programme
September | DJS | Proof all programme content
September | JD | Send Bios&Photos to Directors
September | DJS/JD | Write Media Release
September | JD& Vols | Contact all other media
September | JD & Vols | Contact Seniors, Service groups
September | JD | Create Tickets
September | DJS | Update Dunedin Invite List
September | DJS/JD | Liaise with Vols - lots
September | JD/BP | Send Invites
September | JD | Prepare Money plastic bags
September | DJS/JD | Finalise Mystery Tour
September | DJS/JD | Write next Media Release
September | JD & Vols | Distribute Media Rel
September | JD & Vols | Social Media 'step up'
September | JD | Create Name Tags
September | JD | Laminate Name Tags
September | DJS | Update & Send Code of Conduct Contract
September | DJS | Update Privacy Act & Copyright Waiver
September | JD | Prepare Farewell Function Tix
September | DJS/JD | Further funding apps
September | JD/BP | Prepare Welcome Packs
September | DJS | Contact Mayor & other VIPS
September | JD | Print Certificates
September | JD/BP | Send Invites
September | JD | Collate Invite replies
September | JD | Send Passes to VIPs
September | DJS | Secure Videographer
September | DJS | Secure Photographer
September | DJS/JD | Secure Crew
September | DJS | Prepare Film order forms
September | DJS/JD | Prepare final Info Pack 3
September | DJS | Send E-Mailout
September | JD | Collate info returns
September | DJS | Update Schedules
September | EC/DJS | Check on Travel arrangements
September | DJS | Appoint Meeters & Greeters
September | DJS | Finalise Tolcarne spaces
September | DJS | Confirm MT logistics
September | DJS | Contact New World
September | DJS/JD | Update Merchandise Form
September | DJS | Contact Sheet
September | DJS | Questionnaire YSC
September | DJS | Selection Policy
September | JD | Sele List of students Exploded
September | DJS/JD | Bed Allocation
September | JD | Bed individual signs
September | JD/BP | Groups for games game
September | DJS | Quiz
September | JD/AS | D Game
September | JD/AS | Charades
September | JD/Vols | Increase Social Media PR
September | JD | RollsComments List
September | JD | Daily Shopping Order Form
September | JD | Name tag for Supervisors
September | JD | Name tags for Dirs
September | JD | Name tags for Tutors
September | JD | Name tags for crew
September | JD | Send out Farewell Function tix
September | JD | Dorm lists X 3 types
September | JD | Make Rehearsal Room signs
September | JD | Make Staff Toilet signs
September | DJS | Initial prep of Play Bill
September | JD | Send Tix
September | JF/Vols | Posters & Flyer Street walking
September | AR/JF | Price plaques
September | AR/JF | Prepare Costumes
September | AR/DJS | Director Packs
September | DJS | Confirm Food Driver
September | DJS | Secure Volunteers
September | JD | Create Volunteer Name Tags
September | JD | Make List of VIPs for each perf
September | Dun Vols Alums | Accom&churches Flyers&Posters
September | JD/DJS | Print everything & Photocopy
September | DJS | Charge EFTPOS Machines
September | DJS | Take List
September | JD/DJS | Asssemble Take List items
September | DJS | Obtain Float DJS from home
September | DJS | Arrange Drivers for Shopping etc
September | DJS & JD | Fly to Dunedin
September | DJS/TR | Stationery&Staff/Stud Food Shopping Trip
September | DJS/JD/Dirs | Perf Site Visit
September | DJS/JD | Finish Playbill during event
September | DJS | Print Playbill during event
October | All | Performances
October | DJS & JD | Fly back to Wellington
October | JD/DJS | Narrative Reporting
October | DJS | Thank Yous
October | DJS | Advise YSC selecteds
October | JD/BP/Vols | Social and print media of seles
October | DJS | Letters to all students
October | DJS/JD | Reg Forms & Contracts for YSC 2025
October | DJS | Payments
October | DJS/JD | Order Merchandise
October | JD | Promote photo and videos
October | JD | Collate Video orders & Send out
October | DJS | I&E Report
October | DJS/JD | Reports to funders
October | BP | Summarise Students Reports- AOS
October | DJS/JD | Send Collated Reports to Dirs
October | DJS/JD | Book venue for SGCNZ NSSP 2026